## Project Milestones
Milestone_ID | Milestone_Name | Stage | Status | Verification_Criteria | Verified_Evidence_SHA | Date_Verified | Notes
M-V1-01 | Symphony V1 Autonomy Pipeline Technical Ready | Core V1 Closed-Loop | VERIFIED_CLOSED | Cross-host execution cycle verified via SMB coordination | dee6c76b04b | 2026-09-13 | Windows PC2 (DESKTOP-JDPRUGR) & Mac Chief (MAC_CHIEF_01) authoritative closure
M-V1-02 | Active Ledger & Deduplication Motor | V1 Step 1 | VERIFIED_OPERATIONAL | Single-writer locking, SHA-256 dedupe, 30+ modules verified | f425d328561 | 2026-09-30 | Documented in WINDOWS_VERIFICATION_LEDGER.md; zero double-spend
M-V1-03 | Reliable Automation & Autonomous Level 6 Loop | V1 Step 2 | VERIFIED_OPERATIONAL | Level 6 loop, state reconciliation, unattended crash/quota recovery | 0a82c15259 | 2026-10-08 | Automated crash/quota recovery and state reconciliation in PR #247
M-V1-04 | Golden Path Verification Harness | V1 Step 3 | VERIFIED_OPERATIONAL | 11/11 Golden harness passes, 2 sequential units, controller restart survival | f425d328561 | 2026-10-08 | PR #227 (two units sequential), PR #233 (restart survival), PR #240 (non-stall)
M-V1-05 | Desktop Hub & Founder Project Base | V1 Step 4 | VERIFIED_IN_LANE | Founder Project Base vertical slice (Issue #55 L5), bounded event reads | f425d328561 | 2026-10-07 | PR #226 (vertical slice), PR #230 (bounded event & controller reads)
M-V1-06 | Windows Launcher & Courier.exe | V1 Step 5 | IN_PROGRESS | CourierLauncher.cs Job Object wrapper, user-task service registration | f425d328561 | 2026-10-08 | PR #246 (user task service registration); launcher builds with build_launcher.ps1
M-V1-07 | Clean-Machine Acceptance | V1 Step 6 | IN_PROGRESS | Zero API key in source, verified uninstall without orphaned plists/tasks | f425d328561 | 2026-10-08 | PR #228 (no API key in source), PR #238 (mac uninstall), PR #244, lane/L6-uninstall-verified
M-V1-08 | Real Adapters & Multihost Federation | V1 Step 7 | VERIFIED_IN_LANE | Mac worker adapter flake fix, Windows worker adapter, Google Builder adapter | 0a82c15259 | 2026-10-08 | PR #236 (mac adapter race fix), PR #247 (Google builder worker adapter)
M-V1-09 | Desktop Robot Overlay UI Polish | V1 Step 8 | VERIFIED_CLOSED | Desktop robot overlay UI polish merged into integration/v1 | PR-122 | 2026-10-06 | PR #122 merged; complete overlay visual refinement
M-REV-01 | Commercial Milestone 1 (€1 Verified Revenue) | Post-V1 Commercial | NOT_STARTED | First legitimate commercial customer transaction processed | GATED_ON_V1 | Pending | Zero unverified money; gated by V1 technical acceptance
M-REV-02 | Commercial Milestone 2 (€239 Cumulative Revenue) | Post-V1 Commercial | NOT_STARTED | Cumulative customer cashflow positive validation | GATED_ON_M1 | Pending | Post-V1 revenue scale target; flywheel self-funding milestone
M-REV-03 | Revenue Engine RV-01 (Automated PDF Export) | Revenue Engine | IN_PROGRESS | Report generator with PDF export code integrated | 2a83c198 | 2026-10-05 | Awaiting weasyprint dependency review / approval
M-REV-04 | Revenue Engine RV-02 (AI Marketplace Pilot) | Revenue Engine | VERIFIED | Kibey marketplace pilot package generation | PR-81 | 2026-10-04 | PR #81 merged into integration/v1
M-REV-05 | Revenue Engine RV-03 (Crypto Security Audits) | Revenue Engine | VERIFIED | Autonomous audit generation for open crypto repositories | OPUS-REV3 | 2026-10-05 | 3 sample reports generated (Hunter, AUTOBOT-RAYR-QUANT, cosmicforge-bot)
M-REV-06 | Revenue Engine RV-04 (Automated Code Quality Report) | Revenue Engine | VERIFIED | Autonomous quality analysis with legal guardrails | 6f6dd232 | 2026-10-03 | Report rrc-2 + Legal Guard committed
M-REV-07 | Revenue Engine RV-07 (Data Connector Bridge) | Revenue Engine | VERIFIED | Data connector pilot vertical slice | PR-82 | 2026-10-04 | PR #82 merged into integration/v1
M-REV-08 | Revenue Engine RV-09 (Spreadsheet Cleanup Slice) | Revenue Engine | VERIFIED | courier_runtime.workbook OpenXML cleaner; 8/8 tests green | PR-80/PR-220 | 2026-10-08 | Standard library only, verified in PR #80 and PR #220

## Ledger Workkeys
Workkey | Owner_Lane | Active_Worker | Scope_Module | Base_SHA | Branch | Status | Verification_Level | Notes
L3-GOOGLE-BUILDER-WORKER | Lane L3 Worker | Antigravity (Mac) | scripts/run_autonomous_loop.py | 0a82c15259 | lane/L3-google-builder-worker | ACTIVE_PR_247 | VERIFIED_TARGETED_TESTS | Integrate Google Builder worker & unattended crash/quota recovery
L6-INSTALL-SERVICE-USER-TASK | Lane L6 Packaging | Lane Worker | scripts/windows_worker/install_service.ps1 | f425d328561 | lane/L6-install-service-user-task | ACTIVE_PR_246 | VERIFIED_IN_CI | Register worker as interactive current user task (not SYSTEM)
L2-RETRY-AUTHORIZED-ONE-ATTEMPT | Lane L2 Controller | Lane Worker | courier_core/controller.py | f425d328561 | lane/L2-retry-authorized-one-attempt | ACTIVE_PR_245 | VERIFIED_IN_CI | Human retry grants one attempt, not leftover budget
L6-MUSE-NIGHT-UNINSTALL-NOT-PROVEN | Lane L6 Packaging | Cursor Worker | scripts/uninstall_macos_muse_night_runner.sh | f425d328561 | cursor/l6-muse-night-uninstall-not-proven-be81 | ACTIVE_PR_244 | VERIFIED_IN_CI | Do not report night job removed while plist remains
L6-RESTART-NOT-PROVEN | Lane L6 Packaging | Cursor Worker | deploy/courier.service | f425d328561 | cursor/l6-restart-not-proven-be81 | ACTIVE_PR_243 | MERGEABLE | Do not report Restarted when launchctl unloaded nothing
L6-AUTONOMY-NOT-RUNNING | Lane L6 Packaging | Cursor Worker | scripts/mac_worker/service.py | f425d328561 | cursor/l6-autonomy-not-running-be81 | ACTIVE_PR_242 | MERGEABLE | Do not report autonomy running when launchctl did not load
L6-BACKUP-NOT-PROVEN | Lane L6 Packaging | Cursor Worker | scripts/backup.sh | f425d328561 | cursor/l6-backup-not-proven-be81 | ACTIVE_PR_241 | MERGEABLE | Do not report backup complete when tar fails
L1-GOLDEN-BLOCKED-UNIT-DOES-NOT-STALL | Lane L1 Integration | L1 Worker | tests/test_golden_harness.py | f425d328561 | lane/L1-golden-blocked-unit-does-not-stall | ACTIVE_PR_240 | VERIFIED_IN_CI | Blocked unit does not stall subsequent work units
MUSE-LEDGER-RUNTIME-DEADLINES | Lane L2 / Ledger | Muse (Windows) | courier_runtime/deadlines.py | f425d328561 | muse/MUSE-ledger-runtime-deadlines | ACTIVE_PR_239 | VERIFIED_IN_CI | Date string coercion and CLI support in runtime deadlines
L6-MAC-UNINSTALL-NOT-PROVEN | Lane L6 Packaging | Cursor Worker | scripts/mac_worker/uninstall.sh | f425d328561 | cursor/l6-mac-uninstall-not-proven-be81 | ACTIVE_PR_238 | VERIFIED_IN_CI | Do not report Mac uninstall when plist remains
L6-STOP-DAEMON-IDENTITY | Lane L6 Packaging | Cursor Worker | deploy/courier-status.sh | f425d328561 | cursor/l6-stop-daemon-identity-be81 | ACTIVE_PR_237 | MERGEABLE | Do not report live daemon pid as stopped
L1-MAC-ADAPTER-FLAKE | Lane L1 Integration | L1 Worker | tests/adapters/test_mac_worker_adapter.py | f425d328561 | lane/L1-mac-adapter-flake | ACTIVE_PR_236 | VERIFIED_IN_CI | Fix mac worker adapter result-file race condition
MUSE-LEDGER-PROVIDER-SURVIVAL | Lane L2 / Ledger | Muse (Windows) | courier_runtime/provider_survival.py | f425d328561 | muse/MUSE-ledger-provider-survival | ACTIVE_PR_235 | VERIFIED_IN_CI | Multi-capability circuit check in provider survival
MUSE-LEDGER-RESOURCE-GOVERNOR | Lane L2 / Ledger | Muse (Windows) | courier_runtime/resource_governor.py | f425d328561 | muse/MUSE-ledger-resource-governor | ACTIVE_PR_234 | VERIFIED_IN_CI | Enable Windows psutil metrics and job accounting
L1-GOLDEN-RESTART-BETWEEN-UNITS | Lane L1 Integration | L1 Worker | tests/test_golden_harness.py | f425d328561 | lane/L1-golden-restart-between-units | ACTIVE_PR_233 | VERIFIED_IN_CI | Results survive controller and worker restart between units
MUSE-LEDGER-PROVIDER-HIBERNATION | Lane L2 / Ledger | Muse (Windows) | courier_runtime/provider_hibernation.py | f425d328561 | muse/MUSE-ledger-provider-hibernation | ACTIVE_PR_232 | VERIFIED_IN_CI | Harden hibernation deserialization, add load_continuation
L2-TASKPACKET-PARK-WAKE-SINGLE-WRITER | Lane L2 Controller | L2 Worker | courier_core/task_packet.py | f425d328561 | lane/L2-taskpacket-park-wake-single-writer | ACTIVE_PR_231 | VERIFIED_IN_CI | Host-pressure park/wake never creates a second CURRENT writer
L5-HUB-BOUNDED-READS | Lane L5 Desktop Hub | L5 Worker | courier_hub/app.py | f425d328561 | lane/L5-hub-bounded-reads | ACTIVE_PR_230 | VERIFIED_IN_CI | Bounded event and controller reads in desktop hub
MUSE-LEDGER-PROVIDER-CIRCUIT | Lane L2 / Ledger | Muse (Windows) | courier_runtime/provider_circuit.py | f425d328561 | muse/MUSE-ledger-provider-circuit | ACTIVE_PR_229 | VERIFIED_IN_CI | Synchronize shared breaker restore, classify None/types
L6-BOOTSTRAP-CREDENTIAL-TRUTH | Lane L6 Packaging | L6 Worker | scripts/windows_worker/bootstrap.py | f425d328561 | lane/L6-bootstrap-credential-truth | ACTIVE_PR_228 | VERIFIED_IN_CI | Windows bootstrap: never write API key into source tree
L1-GOLDEN-TWO-UNITS-SEQUENTIAL | Lane L1 Integration | L1 Worker | tests/test_golden_harness.py | f425d328561 | lane/L1-golden-two-units-sequential | ACTIVE_PR_227 | VERIFIED_IN_CI | Two authorized units complete back-to-back with no manual handoff
L5-DESKTOP-HUB-PROJECT-BASE | Lane L5 Desktop Hub | L5 Worker | courier_hub/routes/project_base.py | f425d328561 | lane/L5-desktop-hub-project-base | ACTIVE_PR_226 | VERIFIED_IN_CI | Founder Project Base vertical slice (Issue #55 L5)
MUSE-LEDGER-HOST-GUARDIAN | Lane L2 / Ledger | Muse (Windows) | courier_runtime/host_guardian.py | f425d328561 | muse/MUSE-ledger-host-guardian | ACTIVE_PR_225 | VERIFIED_IN_CI | Harden HostGuardian disk path, swap jitter, cleanup latch
L5-HUB-UNDECODABLE-STATE | Lane L5 Desktop Hub | L5 Worker | courier_hub/routes/home.py | f425d328561 | lane/L5-hub-undecodable-state | ACTIVE_PR_224 | MERGEABLE | Undecodable or unmapped task state never takes Home down
MUSE-LEDGER-GEN-OPENAPI | Lane L2 / Ledger | Muse (Windows) | scripts/generate_openapi.py | f425d328561 | muse/MUSE-ledger-gen-openapi | ACTIVE_PR_223 | VERIFIED_IN_CI | Correct param conversion, import-safe openapi generator
MUSE-LEDGER-GH-CONTRACT | Lane L2 / Ledger | Muse (Windows) | courier_runtime/gh_contract.py | f425d328561 | muse/MUSE-ledger-gh-contract | ACTIVE_PR_222 | VERIFIED_IN_CI | Pin 429 safe-retry contract; verify customer-contract unit
MUSE-LEDGER-CHECK-SAFETY | Lane L2 / Ledger | Muse (Windows) | scripts/check_safety.py | f425d328561 | muse/MUSE-ledger-check-safety | ACTIVE_PR_221 | VERIFIED_IN_CI | Scrub credential shapes from safety finding text
MUSE-LEDGER-SPREADSHEET-SAMPLE | Lane L2 / Ledger | Muse (Windows) | scripts/spreadsheet_cleanup_sample.py | f425d328561 | muse/MUSE-ledger-spreadsheet-sample | ACTIVE_PR_220 | VERIFIED_IN_CI | Correct demo fixture message; verify sample bounds
MUSE-LEDGER-HOST-BUDGETS | Lane L2 / Ledger | Muse (Windows) | courier_runtime/host_budgets.py | f425d328561 | muse/MUSE-ledger-host-budgets | ACTIVE_PR_219 | VERIFIED_IN_CI | Clarify checkpoint-service executor contract
MUSE-LEDGER-POISON-TEST | Lane L2 / Ledger | Muse (Windows) | tests/poison_test.py | f425d328561 | muse/MUSE-ledger-poison-test | ACTIVE_PR_218 | VERIFIED_IN_CI | Remove empty poison_test.py residue
INTAKE-DISPATCHER-VERIFIED | Lane L2 / Ledger | Windows PC2 | scripts/intake_dispatcher.py | dee6c76b04b | integration/v1 | VERIFIED_BASE | 100%_COVERAGE | Corrupt state auto-recovery, missing keys handling verified
RESOURCE-POLICY-VERIFIED | Lane L2 / Ledger | Windows PC2 | scripts/resource_policy.py | dee6c76b04b | integration/v1 | VERIFIED_BASE | 100%_COVERAGE | TaskLeaseManager OS locking, CostGate, FileManifestTracker dedupe
AUTONOMOUS-LOOP-VERIFIED | Lane L3 Host | Windows PC2 | scripts/run_autonomous_loop.py | dee6c76b04b | integration/v1 | VERIFIED_BASE | 100%_COVERAGE | Level 6 loop locking, human gate respecting, task delegation

## Open PRs & CI
PR_Number | Title | Head_Branch | Author | Mergeable | Overall_CI | Reality_Gate | Courier_v1_CI | Blockers | Target_Branch
259 | [L3] gemini_worker_adapter: cross-process central_state lock and atomic persistence | lane/L3-gemini-adapter-central-lock | happyhippovip | MERGEABLE | PENDING | NONE | SUCCESS | None | integration/v1
258 | fix(grants): refuse unknown access/data_class instead of KeyError | muse/grants-unknown-dimension-failclosed | happyhippovip | MERGEABLE | PENDING | NONE | SUCCESS | None | integration/v1
257 | fix(health): truthful customer check on canonical /v1/health | muse/courier-health-truth | happyhippovip | MERGEABLE | FAILURE | NONE | FAILURE | CI check failed | integration/v1
256 | [L6] mac_worker: truthful launchctl status without grep and verified install registration | lane/L6-mac-worker-verified-install-status | happyhippovip | MERGEABLE | PENDING | NONE | SUCCESS | None | integration/v1
255 | [L5] hub: honest installation state from the shared install contract | lane/L5-hub-install-status | happyhippovip | MERGEABLE | PENDING | NONE | SUCCESS | None | integration/v1
254 | Do not report the packaged uninstall complete when removal fails | cursor/l6-dist-uninstall-not-proven-be81 | happyhippovip | MERGEABLE | FAILURE | NONE | FAILURE | CI check failed | integration/v1
253 | Do not report the packaged install successful when copy fails | cursor/l6-dist-install-not-proven-be81 | happyhippovip | MERGEABLE | FAILURE | NONE | FAILURE | CI check failed | integration/v1
252 | docs(ledger): unattended permissions preflight for Courier work units | muse/MUSE-unattended-preflight | happyhippovip | MERGEABLE | PENDING | NONE | SUCCESS | None | integration/v1
251 | Do not report a launcher build when Courier.exe was not written | cursor/l6-launcher-build-not-proven-be81 | happyhippovip | MERGEABLE | FAILURE | NONE | FAILURE | CI check failed | integration/v1
250 | [L2] install state contract: evidence-derived installer states shared by Windows and macOS | lane/L2-install-state-contract | happyhippovip | MERGEABLE | PENDING | NONE | SUCCESS | None | integration/v1
249 | feat(continuation): multi-mode continuation engine and two-unit sequential handoff protocol | muse/MUSE-ledger-verified-continuation | happyhippovip | MERGEABLE | IN_PROGRESS | NONE | IN_PROGRESS | None | integration/v1
248 | [L6] uninstall: verify removal instead of printing unconditional success | lane/L6-uninstall-verified | happyhippovip | MERGEABLE | PENDING | NONE | SUCCESS | None | integration/v1
247 | [L3] Integrate Google Builder Worker & Unattended Crash/Quota Recovery in Autonomous Loop | lane/L3-google-builder-worker | happyhippovip | MERGEABLE | PENDING | NONE | SUCCESS | None | integration/v1
246 | [L6] install_service: register worker as current user (not SYSTEM) and verify registration | lane/L6-install-service-user-task | happyhippovip | MERGEABLE | PENDING | NONE | SUCCESS | None | integration/v1
245 | [L2] Human retry grants one attempt, not the leftover budget | lane/L2-retry-authorized-one-attempt | happyhippovip | MERGEABLE | PENDING | NONE | SUCCESS | None | integration/v1
244 | Do not report the Muse night job removed while the plist remains | cursor/l6-muse-night-uninstall-not-proven-be81 | happyhippovip | MERGEABLE | PENDING | NONE | SUCCESS | None | integration/v1
243 | Do not report Restarted when launchctl unloaded nothing | cursor/l6-restart-not-proven-be81 | happyhippovip | MERGEABLE | FAILURE | NONE | FAILURE | CI check failed | integration/v1
242 | Do not report autonomy services running when launchctl did not load | cursor/l6-autonomy-not-running-be81 | happyhippovip | MERGEABLE | FAILURE | NONE | FAILURE | CI check failed | integration/v1
241 | Do not report a backup complete when tar fails | cursor/l6-backup-not-proven-be81 | happyhippovip | MERGEABLE | FAILURE | NONE | FAILURE | CI check failed | integration/v1
240 | [L1] Golden proof: blocked unit does not stall the next units | lane/L1-golden-blocked-unit-does-not-stall | happyhippovip | MERGEABLE | PENDING | NONE | SUCCESS | None | integration/v1
239 | fix(ledger): date string coercion and CLI support in runtime deadlines; verify unit | muse/MUSE-ledger-runtime-deadlines | happyhippovip | MERGEABLE | PENDING | NONE | SUCCESS | None | integration/v1
238 | Do not report Mac uninstall when the plist remains | cursor/l6-mac-uninstall-not-proven-be81 | happyhippovip | MERGEABLE | PENDING | NONE | SUCCESS | None | integration/v1
237 | Do not report a live daemon pid as stopped | cursor/l6-stop-daemon-identity-be81 | happyhippovip | MERGEABLE | FAILURE | NONE | FAILURE | CI check failed | integration/v1
236 | [L1] Fix mac worker adapter result-file race (test_run_success flake) | lane/L1-mac-adapter-flake | happyhippovip | MERGEABLE | PENDING | NONE | SUCCESS | None | integration/v1
235 | fix(ledger): multi-capability circuit check in provider_survival; verify unit | muse/MUSE-ledger-provider-survival | happyhippovip | MERGEABLE | PENDING | NONE | SUCCESS | None | integration/v1
234 | fix(ledger): enable Windows psutil metrics, job accounting in resource_governor; verify unit | muse/MUSE-ledger-resource-governor | happyhippovip | MERGEABLE | PENDING | NONE | SUCCESS | None | integration/v1
233 | [L1] Golden: results survive controller and worker restarts between two units, no duplicate effects | lane/L1-golden-restart-between-units | happyhippovip | MERGEABLE | PENDING | NONE | SUCCESS | None | integration/v1
232 | fix(ledger): harden hibernation deserialization, add load_continuation; verify unit | muse/MUSE-ledger-provider-hibernation | happyhippovip | MERGEABLE | PENDING | NONE | SUCCESS | None | integration/v1
231 | [L2] TaskPacket: a host-pressure park/wake never creates a second CURRENT writer | lane/L2-taskpacket-park-wake-single-writer | happyhippovip | MERGEABLE | PENDING | NONE | SUCCESS | None | integration/v1
230 | [L5] Hub: bounded event and controller reads | lane/L5-hub-bounded-reads | happyhippovip | MERGEABLE | PENDING | NONE | SUCCESS | None | integration/v1
229 | fix(ledger): synchronize shared breaker restore, classify None/types; verify unit | muse/MUSE-ledger-provider-circuit | happyhippovip | MERGEABLE | PENDING | NONE | SUCCESS | None | integration/v1
228 | [L6] Windows bootstrap: never write the API key into the source tree; truthful health check | lane/L6-bootstrap-credential-truth | happyhippovip | MERGEABLE | PENDING | NONE | SUCCESS | None | integration/v1
227 | [L1] Golden: two authorized units complete back-to-back with no manual handoff | lane/L1-golden-two-units-sequential | happyhippovip | MERGEABLE | PENDING | NONE | SUCCESS | None | integration/v1
226 | feat(hub): Founder Project Base vertical slice (Issue #55 L5) | lane/L5-desktop-hub-project-base | happyhippovip | MERGEABLE | PENDING | NONE | SUCCESS | None | integration/v1
225 | fix(ledger): harden HostGuardian disk path, swap jitter, cleanup latch; verify unit | muse/MUSE-ledger-host-guardian | happyhippovip | MERGEABLE | PENDING | NONE | SUCCESS | None | integration/v1

## Worker Fleet Status
Worker_Agent | Host_Platform | Role | Assigned_Lanes | Current_Status | Resource_Limits_and_Safety | Primary_Deliverables | Failure_Mode_Guard
Anthropic Claude / Muse | Windows 10 (DESKTOP-JDPRUGR) | Windows Steward & Read-Only Auditor | L2 Ledger, Policy, Deadlines, Governor | ACTIVE | 12-slot power pool budget; max memory 88%; no ad-hoc installations | PR #218-#223, #225, #229, #232, #234, #235, #239 (12+ verified PRs) | Context rotation before hard_threshold_failed; no bulk permission menu clicking
Google Antigravity | macOS (MacBook Pro, Intel Core i7) | Primary Product Builder & Google Worker Integrator | L3 Worker Host, L5 Desktop Hub, L6 Packaging | ACTIVE | Host bounded: single process when swap > 10GB; CPU throttling guard | PR #247 (Google Builder integration & unattended loop), Cross-Platform Excel Dashboard | Strict NO-GREP execution rule; single-writer fencing; turn-based auto-continuation
Cursor AI Worker | Cross-Platform (macOS / Windows) | Targeted L6 Service & Process Hygiene Fixer | L6 Packaging, Launchctl, Service Registration | ACTIVE | Single-scope branches; truthful command outcome validation | PR #237 (daemon identity), #238 (mac uninstall), #241 (backup), #242 (running), #243 (restart), #244 (plist) | Do not report actions complete without concrete proof of command outcome
OpenAI Codex | Cloud Runner / CI | Provider Continuity & Automated Code Reviewer | L10 Reviewer Bridge (courier-codex-bridge) | MERGED_IDLE | Gated reviewer in resource_policy.py; read-only code analysis | PR #128 (codex/provider-continuity-resume merged into integration/v1) | Fail-closed if API key missing; strictly read-only reviewer
xAI Grok | Cloud / Web | Market Opportunity & Competitor Intelligence | Opportunity Radar / Strategic Research | ADVISORY_COMPLETE | Zero write access to repo; read-only dossier generation | Research dossiers: Malta Cliffs Top 10, Multitalent Energy Top 10 in project memory | Customer never operates external models; advisory only

## Packaging & Installers
Component | Platform | Artifact_Type | Source_Path | Current_Status | Verification_Method | Known_Gaps_or_Blockers
CourierLauncher.cs | Windows 10/11 | C# .NET Executable Wrapper (Courier.exe) | scripts/windows_worker/launcher/build_launcher.ps1 | VERIFIED_SOURCE | Wraps Courier.exe, catches Ctrl+C, calls /v1/shutdown, terminates children via Win32 Job Object | Requires clean-machine compile test on fresh Windows machine
Windows Worker Service | Windows 10/11 | PowerShell Service Setup Script | scripts/windows_worker/install_service.ps1 | PR_246_ACTIVE | Registers worker as interactive current user scheduled task (not SYSTEM) | PR #246 CI in progress
Windows Installer | Windows 10/11 | Inno Setup Package & PowerShell Installer | scripts/windows_worker/dist/install.ps1 | READY_FOR_TEST | Preserves courier.db and logs on uninstall; removes config.json and run/ directory | Needs automated clean-machine acceptance test
Windows Uninstaller | Windows 10/11 | PowerShell Verified Teardown Script | scripts/windows_worker/dist/uninstall.ps1 | VERIFIED_IN_LANE | Verifies task, path, and Courier.exe removal before reporting success | Covered in PR #246 and branch lane/L6-uninstall-verified
macOS Muse Night Runner | macOS | Launchd Plist Daemon Installer | scripts/install_macos_muse_night_runner.sh | VERIFIED_SOURCE | Installs com.courier.muse.night.plist for bounded nightly cron runs | PR #244 verifies plist removal on uninstall
macOS Worker Service | macOS | Shell / Launchd Service Script | scripts/mac_worker/install.sh | VERIFIED_SOURCE | launchctl load/unload with single-process PID fencing | PR #238 / #242 / #243 ensure truthful launchctl status
Mac Runtime Environment | macOS | Shell Runtime Provisioner | deploy/install_mac_runtime.sh | READY | Sets up python/node execution environment | Bound by Mac Intel memory / swap constraints
Surface Budget Controller | Cross-Platform | Python Runtime Guardian | courier_runtime/surfaces.py | VERIFIED_COMMITTED | Prevents terminal storms (e.g. 64 windows) by enforcing admit() budget check | Committed in 3d5713c2; 18 unit tests green

## Costs & Budget
Provider_or_Resource | Entitlement_Tier | Billing_Policy | Spend_To_Date_EUR | Budget_Cap_EUR | Gating_Mechanism | Quota_and_Rate_Limit_Action
GitHub Actions CI | Free Tier (Public/Repo) | ZERO_COST_ONLY | 0 | 0 | Concurrency caps; fail-closed on rate limit | Bounded workflow runs; no extra minutes purchased
Google Antigravity Builder | Active Google Subscription | ZERO_COST_ONLY | 0 | 0 | Human gate required for plan changes / upgrades | Quota failover: checkpoint state & park without auto-topup
Anthropic Claude / Muse | Retained Subscription | ZERO_COST_ONLY | 0 | 0 | No automatic purchases; no credit card charging | Hard context rotation on limit; wait for scheduled window
OpenAI Codex / ChatGPT | Subscription / Web | ZERO_COST_ONLY | 0 | 0 | Gated by ResourcePolicyManager in scripts/resource_policy.py | Fail-closed if API key missing; read-only review
Local Hardware (MacBook Pro) | Local Compute | Host Resource Budget | 0 | 0 | HostGuardian (RAM & Swap monitoring) | Single-process execution when swap > 10GB
Local Hardware (Windows PC2) | Local Compute | Host Resource Budget | 0 | 0 | ResourceGovernor (psutil job objects) | Window limit: max 12 slots; stop on memory pressure > 85%
Revenue Target: Milestone 1 | Commercial Customer | Revenue Generation | 0 | 1 | Verified customer payment verification | Target: first €1 legitimate revenue
Revenue Target: Milestone 2 | Commercial Customer | Revenue Generation | 0 | 239 | Verified customer payment verification | Target: €239 cumulative revenue self-funding flywheel

## Tests & Evidence
Evidence_ID_or_Suite | Scope_Category | Verification_Status | Test_Count_or_Target | Source_File_or_Digest | Date_Verified | Evidence_Details
TEST-SUITE-FULL | Full Repository Test Suite | VERIFIED | 186 | tests/ | 2026-10-08 | 186 test files passing across Linux and Windows CI runners
GOLDEN-01-HARNESS | Core Autonomy Contract | VERIFIED | 11 | tests/test_golden_harness.py | 2026-10-08 | 11/11 Golden harness tests green; Linux 1433 passed / Windows 1379 passed
GOLDEN-02-SEQUENTIAL | Golden Proof: Two Units | VERIFIED | 2 | lane/L1-golden-two-units-sequential (PR #227) | 2026-10-07 | Two authorized units complete back-to-back with zero manual handoff
GOLDEN-03-RESTART | Golden Proof: Restart Integrity | VERIFIED | 1 | lane/L1-golden-restart-between-units (PR #233) | 2026-10-07 | Results survive controller and worker restart between units, no duplicate effects
GOLDEN-04-NON-STALL | Golden Proof: Pipeline Resilience | VERIFIED | 1 | lane/L1-golden-blocked-unit-does-not-stall (PR #240) | 2026-10-08 | Blocked unit does not stall subsequent work units in pipeline
RUNTIME-WORKBOOK | Standard Library OpenXML Engine | VERIFIED | 8 | tests/test_runtime_workbook.py | 2026-10-08 | 8/8 tests green: read values/formulas, plan mutation, atomic apply, hash verification
GOOGLE-BUILDER-001 | Autonomous Loop Real Execution | VERIFIED | 1 | events/evidence/task-google-builder-live-001_evidence.json | 2026-10-08 | Real Google Builder execution evidence, exit code 0, SHA-256 result verified
GOOGLE-BUILDER-002 | Autonomous Loop Real Execution | VERIFIED | 1 | events/evidence/task-google-builder-live-002_evidence.json | 2026-10-08 | Second consecutive unit, exit code 0, state reconciled in central_state.json
DEDUPE-PREFLIGHT-01 | Deduplication Engine Preflight | VERIFIED | 1 | events/evidence/duplicate_preflight_0226e05a99d440b4.json | 2026-10-07 | Preflight fingerprint match; duplicate task dispatch deterministically avoided
DEDUPE-PREFLIGHT-02 | Deduplication Engine Preflight | VERIFIED | 1 | events/evidence/duplicate_preflight_c42c6830a2b5f3d4.json | 2026-10-07 | Cache reuse validated with SHA-256 integrity and receipt generation
WIN-LEDGER-INTAKE | Windows Ledger Module Intake | VERIFIED | 10 | memory/WINDOWS_VERIFICATION_LEDGER.md | 2026-09-30 | scripts/intake_dispatcher.py: 100% test coverage on Windows
WIN-LEDGER-POLICY | Windows Ledger Resource Policy | VERIFIED | 12 | memory/WINDOWS_VERIFICATION_LEDGER.md | 2026-09-30 | scripts/resource_policy.py: 100% test coverage on Windows
WIN-LEDGER-LOOP | Windows Autonomous Loop Engine | VERIFIED | 8 | memory/WINDOWS_VERIFICATION_LEDGER.md | 2026-09-30 | scripts/run_autonomous_loop.py: 100% test coverage on Windows

## Approvals & Actions
Decision_ID | Topic_Area | Decision_Text | Human_Status | Date_or_Deadline | Policy_or_Evidence_Doc | Next_Safe_Action
D1 | Git Branch Integration | Branch claude/determined-hypatia-uvybo5 in integration/v1 uebernehmen | DONE_MERGED | 2026-10-05 | memory/OPEN_ITEMS_MASTER_CURRENT.md | Merged into integration/v1, no further action needed
D2 | Dashboard Test Suite | 2 veraltete Dashboard-Tests: loeschen oder reparieren | DONE_REPAIRED | 2026-10-05 | memory/OPEN_ITEMS_MASTER_CURRENT.md | Repaired on Windows
D3 | Git History Hygiene | Alte oeffentliche Daten in Commit 48f7b8bb: History umschreiben? | OPEN_DEFERRED | Pending | memory/HUMAN_DECISION_POLICY_CURRENT.md | Erst sichern, dann entscheiden; fragen nur wenn einziger Restpfad blockiert
D4 | Python Version Target | Python 3.11.9 (Bundle) vs 3.12 (CI) vereinheitlichen | APPROVED_3.12 | 2026-10-04 | memory/OPEN_ITEMS_MASTER_CURRENT.md | Standardize packaging on Python 3.12
D5 | Company Vision Direction | Vision-Notiz ('Engineering OS -> Aerospace') speichern? | APPROVED_NORTH_STAR | 2026-10-04 | memory/OPEN_ITEMS_MASTER_CURRENT.md | Nordstern recorded in strategy memory
FAM-01 | Family Accident Questionnaire | hkk Unfallfragebogen (Mama Sturz 27.09) | DONE_SUBMITTED | 2026-10-04 | memory/OPEN_ITEMS_MASTER_CURRENT.md | Eingereicht; auf moegliche hkk-Rueckfrage achten
FAM-02 | Residence Registration Status | Meldestatus beim Buergerbuero klaeren | READY_TO_SEND | vor 27.10.2026 | memory/OPEN_ITEMS_MASTER_CURRENT.md | Senden durch Dennis ueber Windows-Familien-Chat
FAM-03 | Care Level PG4 Objection | Widerspruch PG4 - 2. Ergaenzung (Entlassbrief 27.09.-02.10.) | NEEDS_SOURCE | Bald | memory/OPEN_ITEMS_MASTER_CURRENT.md | Entlassbrief-Foto bereitstellen; kein Handlungsbedarf im Courier-Repo
POL-01 | Human Question Policy | Keine Bulk-Frageboegen; nur 1 kleinste Frage wenn einziger Pfad blockiert | ACTIVE_BINDING | 2026-10-04 | memory/HUMAN_DECISION_POLICY_CURRENT.md | Strict rule: Dennis is not the message bus
NEXT-01 | Cross-Platform Excel Dashboard | Deliver editable .xlsx workbook to reports/ and 2026-project-memory | IN_PROGRESS | 2026-10-08 | Current Task | Generate, validate, and verify .xlsx workbook across macOS and Windows
NEXT-02 | Google Builder PR Landing | Merge PR #247 (lane/L3-google-builder-worker) into integration/v1 | PENDING_CI | 2026-10-08 | GitHub PR #247 | Monitor CI checks and L1 integration merge sequence